Equality, Diversity & Inclusion
Year End Report 2025-26

Executive Summary
We are committed to improving our approach to understanding our tenants needs, delivering outstanding services and are focused on embedding equality and diversity into the services we deliver. Our Landlord Panel requested that our progress would be monitored through a six-monthly report.
This report contains information on the following:
1. Executive summary
2. Update on progress since last report in September 2025
3. Planned activity up to the end of September 2026/27
2025-26 Highlights since the last report
- We have continued to refresh our customer data following the exercise undertaken earlier and are actively addressing gaps in our dataset and have achieved 94.91% against our target of 90%
- Improvements have been implemented to our IT systems to ensure that all demographic data collected is recorded and stored appropriately, supporting inclusive and diverse service delivery.
- Staff have received training on the recent IT system enhancements, ensuring that the new customer data collection methodology has been rolled out to our Housing team.
- We have published our new Engagement Strategy which includes a commitment to improve the diversity of our engaged tenants
- We have undertaken further research to align customer profile data to performance reporting, particularly with regards to complaints analysis
- We have produced a Learning from Complaints Report which included consideration of the demographic diversity of complainants
- We have worked with colleagues in the People Team to develop refresher training for our teams to help them better understand and respond appropriately to diversity issues, cultural differences and communications needs. This training was delivered during February, March and April 2026.
2026-27 Areas of further focus
- Continuing our efforts to increase the quality of information we hold about our tenant and their households.
- To continue to progress with our culture change journey ensuring that all staff understand our approach to Equality, Diversity and Inclusion: Housing and Property Services are passionate about providing a service that is:
  - Accessible, fair and equitable
  - Designed around the needs of all communities
  - Adaptable to cultural, religious, linguistic and accessible requirements
  - Creates trust and improves outcomes
Progress against our key objectives since September 2025
To provide assurance that we continue to demonstrate our commitment to equality and diversity across our service, we set three key objectives for 2025-26
  1. Continue to improve our customer information with the aim of achieving 90% by the end of 2025-26
  2. Complete a data cleanse of the information held in our IT systems ahead of the implementation of our new Unified Housing and Property Management System scheduled for early 2026/27
  3. Develop and roll out a training programme specifically aimed at supporting our staff to understand and respond appropriately to diversity issues, communications needs and cultural differences.
This section sets out our progress towards these key objectives.
    1. Continue to improve our customer information with the aim of achieving 90% by the end of 2025-26
We have made further improvements to our approach to collecting tenant information; as well routinely checking with tenants through our Tenancy Home Visits we encourage all staff to update demographic information, when appropriate, during every contact.
Since the last report we have carried out a review of the way we record demographic and customer information. As a result, we have implemented updates to our IT systems to ensure that all demographic data collected is recorded and stored appropriately, supporting inclusive and diverse service delivery.
Staff have received training on the recent IT system enhancements.
We have consulted with managers and colleagues in the corporate Equalities Group and agreed to include those who have told us that they ‘prefer not to say’ in the overall figures for information collated as it is a legitimate choice for customers. This has helped to increase our overall rate of information recorded.
We have also collated and where possible, in compliance with data protection legislation, have transferred information held in other IT systems into our NEC Housing and Property Services Management System.
As a result of the work we have undertaken, helped by the data cleanse exercise (see below) we have exceeded our target of 90% customer information held by the end of 2025-26; we currently hold 94.91% of the necessary customer information now recorded in NEC.
The table below shows a breakdown of the information we hold in our system for each of the protected characteristics:
	Not Recorded	Recorded
Gender Identity	0.00%	100.00%
Religion or faith	22.00%	78.00%
Age	0.00%	100.00%
Disability or long-term limiting illness	1.93%	98.07%
Ethnic origin	3.68%	96.32%
Sexual Orientation	7.45%	92.55%
Communications Preferences	4.84%	95.16%
Language	0.76%	99.17%
Overall	5.08%	94.91%

    1. Complete a data cleanse of the information held in our IT systems ahead of the implementation of our new Unified Housing and Property Management System scheduled for early 2026/27
Our second objective of completing the data cleansing exercise ahead of the implementation of our new integrated ICT system is progressing. The system enhancements that have been completed have necessitated the deletion of some historic data and other data being moved from fields that were being used inappropriately for the storage of personal data. As a result of this the amount of data we held about our tenants with regards to disabilities and long-term limiting illnesses and their language preferences was initially reduced. The data matching exercise described above has helped us to fill some of the gaps. We are confident that the information we now hold is more accurate and up to date.
    1. Develop and roll out a training programme specifically aimed at supporting our staff to understand and respond appropriately to diversity issues, communications needs and cultural differences.
We have worked with colleagues in the People Team to develop refresher training for our teams to help them better understand and respond appropriately to diversity issues, cultural differences and communications needs.
Two methods of delivery were developed; face to face ‘train the trainers’ training for managers, team leaders and some staff in the Housing Neighbourhood and Housing Options teams who are required to deliver the training to their teams, and toolbox talks for those in our Housing Property Services. This training was delivered during February, March and April 2026 with 30 colleagues attending the face-to-face training.
Planned Activity for 2026-27
We are pleased with our progress to date; however, we know that we have more work to do. In the next six-months of 2026-27, we will be focusing on delivering the following:
- Further improving the amount and quality of the data we hold by:
  - As part of the consultation regarding proposed improvements to our Tenancy Agreement, we are taking the opportunity to ask all tenants to provide up to date information regarding the protected characteristics of their household.
  - Collecting information about protected characteristics and communications needs during each Tenancy Home Visit
  - Continue to provide training to highlight the importance of updating information for front line staff and contact centre
  - Aim towards the implementation of an improved Housing and Property Services IT system to improve data management
  - Raise awareness of the importance of ensuring our data is up to date and how it is every officer’s responsibility
- Complete Equality Impact Assessments (EQiA’s) in line with Council Policy and Procedures.
By the end of 2026-27 we have set ourselves the following key objectives.
  1. Continue to improve our customer information with the aim of achieving 96% by the end of 2026-27
  2. Complete the data cleanse of the information held in our IT systems ahead of the implementation of our new Unified Housing and Property Management System scheduled for 2026/27
  3. Develop and roll out procedures to ensure we use every contact with our customers as an opportunity to check and update the information we hold about them